## Sheet1
Feature ID | Engine Version | Feature Name | Iteration | Description | Complexity Estimate | Priority | Dependencies Estimate | Status | Feature ID | Editor Version | Feature Name | Iteration | Description | Complexity Estimate | Priority | Dependencies Estimate | Status
| 0.1 | ECS Systems and Modules | 2 | Simplifying declaration and definition of systems and modules. System functions are defined inside cpp files and not hpp. Templatezation of systems and modules is minimalized. Module manager imports modules deferred, meaning it first constructs a dependency graph for modules and systems and afterwards actually imports everything into flecs. | Medium | High |  | In Progress |  | 0.1 | World Editor | 1 | Ability to create and edit game worlds. Ability to define layers and paint terrain, place entities and prefabs etc. | Medium | High | Engine 0.1 | On Hold
| 0.1 | ECS Engine Phases | 1 | Integrate flecs predefined system phases into the engine and make them available for system use. Setup engine rendering phases for begin frame, end frame and everything inbetween. | Medium | High |  | On Hold
| 0.1 | SM Resource Management | 1 | Spritemancer managing GPU related resources, such as textures, images and shaders. | Low | Low |  | Done
| 0.1 | Asset Pipeline | 1 | Define asset creation from raw resources and their compilation and publishing process. Moreover define the usage of compiled resources and asset from published game. Track asset dependencies. | High | Medium | Virtual File System | On Hold
| 0.1 | Plugins | 1 | Define plugin usage, such as loading and unloading and their location. Plugins should have the possibility to be hot-reloaded and add or remove RTTR types such as components or systems. | High | High | Asset Pipeline | On Hold
| 0.1 | Profiler | 1 | In-Engine profilers and data gatherers for monitoring memory usage and statistics, CPU usage and statistics, GPU memory usage and statistics. Moreover we want detailed usage graphs for what the memory is being used and where the CPU is spending most of its time. | Medium | Medium |  | On Hold
| 0.1 | Virtual File System | 1 | Formalize the usage of the virtual file system inside the engine. Adding an removing aliases. Opening, finding and closing files. | Medium | High |  | On Hold
| 0.1 | Camera System | 1 | Implementing camera system features, such as following an entity, edge snapping, camera window, smooth position changes, projected focus, target focus, camera path, zoom to fit, attractors and detractores, region focus, gesture focus, cinematic paths, multi focal, manual control, camera shake, average oriented region, cues etc. (For more info see spritemancer sm_config.hpp) | Medium | Low |  | On Hold
| 0.1 | HID Input | 1 | Receiving and working with input from keyboard, mouse, joystick and gamepad. | Medium | Low |  | On Hold
| 0.2 | Streaming | 1 | Dynamically loaded and unloaded resources in-game depending on requirement. Resources can be unloaded when they are not required anymore and loaded when they become required. | High | Low | Asset Pipeline, Plugins | On Hold
| 0.2 | AI Pathfinding | 1 | Representation of a navigation graph. Finding a path from A to B in that graph. | High | Low | Asset Pipeline, Plugins | On Hold
| 0.2 | AI Behavior Trees | 1 | Definition and representation of BTs. Attaching BTs to entities and executing logic for them. | High | Low | Asset Pipeline, Plugins | On Hold
| 0.3 | Scripting | 1 |  | Medium | Low | Asset Pipeline, Plugins, Lua Integration | On Hold
| 0.3 | Lua Integration | 1 | Integrating Lua scripting engine. Exposing engine functionality to Lua. | High | Low | Asset Pipeline, Plugins | On Hold
| 0.4 | Audio and Sound | 1 | Integrating a thirdparty for audio, leaving possibility to replace or extend that thirdparty. Implementing a 2D sound engine that can play sounds, barks and music on different channels with dynamic volume changes. | High | Low | Asset Pipeline, Plugins | On Hold
| 0.4 | Networking | 1 | Integrating thirdparty for networking code. Defining how networking should be done within the engine. | High | Low |  | On Hold
| 0.5 | Testing and Unit Testing | 1 | Unit test launcher application and individual unit tests using a thirdparty. | Medium | Low |  | On Hold
| 0.6 | UI | 1 | In-Game UI solution. | High | Low |  | On Hold
| 0.7 | Physics | 1 | Integrate box2d thirdparty for physics. | Low | Low |  | On Hold